## Overview
ORCHESTRA Student 4-Week Validation Plan
Simulation-only proof-of-concept: laser-welding PdM decision support
Item | Value | Note
Start date | 2026-09-03 | Thursday, Asia/Shanghai
Duration | 4 weeks | 40 h/week, ~160 h total
Goal | Simulation validation + conference draft | No real hardware / no live operator
Scope decision | Drop real-cell + user study to Future Work | Spend weeks on simulation credibility
Protected core | E2, E4, E5, E6, E9 + reproducibility | Cut E7 / multi-algorithm if behind
Language | English only | Zero Chinese in code, comments, paper
Key claim | Coordination architecture, not a new XGBoost/PPO | Auditable + selective review
Success bar | Full ORCHESTRA ~ PPO-only reward, plus audit + selective review | >=5 seeds, 95% CI

## Execution Plan
Weekly Execution Plan (fill Status / Actual result as you go)
Week | Day | Time | Task | Deliverable / Gate | Status
Week 1 | W1D1 | 2 h | Write spec.md: 3 core claims mapped to experiments; 'must NOT claim' list; 4-agent message contract | spec.md committed
Week 1 | W1D2 | 6 h | Build simulation generator: normal + focus-drift; all laser-welding state variables; seeded | raw_stream.csv
Week 1 | W1D3 | 8 h | Implement Machine/IoT Agent: validation + provenance + feature vector + split | feature_vector.csv + provenance tags
Week 1 | W1D4 | 8 h | Implement Gymnasium-like environment: state, 5 actions, reward, resources, feedback | env passes sanity checks
Week 1 | W1D5 | 8 h | Repo + harness: configs, seed control, logging, naive baselines (random + rule) | reproducible at fixed seed
Week 1 | W1D6 | 6 h | Unit tests + 3 diagnostic plots (urgency vs time; feature dist.; reward trace) | plots in report/figures
Week 1 | W1D7 | 2 h | Checkpoint: clean-clone rerun; W1 retrospective | gate passed or scope cut
Week 2 | W2D1 | 8 h | Train XGBoost urgency predictor; 5-fold CV; hyperparameter tuning | CV MAE/RMSE/R2 logged
Week 2 | W2D2 | 6 h | SHAP feature importance; compare to physical expectations | SHAP plots + notes
Week 2 | W2D3 | 8 h | Uncertainty proxy + calibration (ECE, coverage) | calibration plot
Week 2 | W2D4 | 8 h | Review-trigger logic: thresholds, severity, uncertainty, conflict, resources | review router
Week 2 | W2D5 | 6 h | Review-threshold sweep: rate, override, failures avoided, burden | threshold sweep table
Week 2 | W2D6 | 2 h | Compare no/random/uncertainty/all review at equal budget | E4 result table
Week 2 | W2D7 | 2 h | Checkpoint; archive model + results; update spec.md | gate passed
Week 3 | W3D1 | 8 h | Implement PPO; hyperparameter sensitivity (clip, GAE, LR, entropy) | learning curves >=5 seeds
Week 3 | W3D2 | 6 h | Reward ablation: safety / +downtime / +cost / +load / full | reward ablation table
Week 3 | W3D3 | 8 h | 5 baselines: corrective, periodic, alert-only, rule, PPO-only | baseline table
Week 3 | W3D4 | 8 h | 5 ablations: remove review/PPO/XGBoost/provenance/trigger | ablation table
Week 3 | W3D5 | 6 h | Sensitivity: noise, missing modality, drift, OOD, scarce resources, delay | sensitivity plots
Week 3 | W3D6 | 2 h | Auditability: 100% trace completeness + 10 counterfactuals | audit score + log
Week 3 | W3D7 | 2 h | Checkpoint; freeze all figures and numbers | gate passed
Week 4 | W4D1 | 8 h | Draft introduction + related work + contributions (target template) | Sections 1-2
Week 4 | W4D2 | 8 h | Draft framework + methodology; reproduce key tables | Sections 3-4
Week 4 | W4D3 | 8 h | Draft experiments/results + validation; assemble figures | Sections 5-6
Week 4 | W4D4 | 6 h | Conclusion, limitations, future work; proofread + claim calibration | full draft 8-10 pp
Week 4 | W4D5 | 6 h | Reproducibility package: generator, scripts, configs, logs, Dockerfile, README | archive runs clean
Week 4 | W4D6 | 2 h | Advisor pre-review pass; blocking comments only | review notes
Week 4 | W4D7 | 2 h | Final check: zero Chinese; final commit + tag | v1.0-submission-ready

## Experiment Matrix
Minimum Evidence Set (9 experiments)
Non-negotiable. Fill 'Status' and 'Actual result' as work progresses.
ID | Experiment | Design | Key metric | Week | Status
E1 | Simulation validity | Latent degradation model + induced faults (focus drift, lens contamination, gas, positioning); normal/degradation/OOD splits | Physical plausibility; fault separation | W1
E2 | XGBoost urgency | 5-fold CV; MAE/RMSE/R2; SHAP; compare RF/LightGBM/MLP | Low error; SHAP matches physics | W2
E3 | Uncertainty calibration | Quantile / ensemble / conformal / OOD; ECE + coverage | Error correlates with uncertainty | W2
E4 | Review routing | No-review / random / uncertainty-triggered / all-review at equal budget | Better safety at lower burden | W2
E5 | Full vs baselines | Corrective, periodic, alert-only, rule, PPO-only | Reward + audit + review coverage | W3
E6 | Ablations | Remove review, PPO, XGBoost, provenance, trigger | Each component adds value | W3
E7 | Sensitivity | Noise, missing modality, drift, OOD, scarce resources, delay | Graceful degradation | W3
E8 | Auditability | 100% trace completeness + 10 counterfactuals | Every action reconstructable | W3
E9 | Statistical validity | >=5 seeds; mean +/- 95% CI; paired bootstrap/Wilcoxon | Significant, reproducible | W3

## Checks and Risks
Checkpoints, Risks and Mitigations
Type | Item | Risk / Gate | Mitigation / Decision
Checkpoint | End of Week 1 | Full trace reproducible at fixed seed | If not: stop adding features, fix generator first
Checkpoint | End of Week 2 | XGBoost + calibration + review routing done | If not: cut model comparison, keep XGBoost + uncertainty
Checkpoint | End of Week 3 | Baselines + ablations + statistical significance | If not: protect E2/E4/E5/E6/E9, cut E7
Checkpoint | End of Week 4 | Draft + reproducibility package advisor-ready | If not: cut prose, protect archive + tables
Risk | Overclaiming (real laser / deployment / trust) | Rejection or loss of credibility | Label everything 'simulation proxy'; move real-cell + user study to Future Work
Risk | Single-run results presented as truth | Non-reproducible claims | >=5 seeds, 95% CI, paired tests always
Risk | New algorithm claimed for XGBoost/PPO | Reviewers reject novelty framing | Frame novelty as coordination architecture only
Risk | Chinese text left in deliverables | Reviewer complaint; inconsistent English | Final grep + manual check; all comments/code in English
Risk | Missing modalities / drift not handled | Weak robustness section | E7 sweep; if time short, keep noise + OOD only
Risk | Audit traces incomplete | Cannot prove coordination | Log every message by default; E8 = 100% completeness
Decision | Week 3 behind schedule | Which experiments to drop | Drop E7 settings + multi-algorithm; protect core five + archive
Decision | Paper length exceeds limit | What to compress | Move methodology detail to appendix; keep results + claims