ORCHESTRA: Student 4-Week Validation Plan

A Simulation-Based Human-Centred Multi-Agent Framework for Predictive Maintenance Decision Support in Laser Welding

# 1. Goal Contract

Goal: simulation-only validation of ORCHESTRA, plus a submission-ready conference paper draft. Duration: 4 weeks at ~40 h/week, starting 2026-09-03. Total budget: roughly 160 hours.

The single most important scope decision: drop any claim of real hardware or live-operator validation now, and spend those weeks on (1) a physically credible laser simulation, (2) uncertainty-calibrated selective review, (3) resource-aware PPO scheduling, (4) auditable traces and statistical significance. Real-cell fault injection and an operator user study move to Future Work.

## 1.1 Non-negotiable deliverables

- A reproducible simulation + Gymnasium-like environment, fixed random seeds, config files, environment spec.

- A calibrated XGBoost urgency predictor with uncertainty estimates.

- An uncertainty-triggered Human Operator Agent routing mechanism.

- A context-aware PPO scheduling agent (actions 0-4).

- Full baseline and ablation study with statistical tests (>=5 seeds, 95% CI).

- Robustness and sensitivity analysis.

- Audit-trace evaluation (every decision reconstructable).

- An 8-10 page conference-ready draft + reproducibility package.

## 1.2 What this paper must NOT claim

# 2. The Route (one-line summary)

| Week | Goal | Gate (must pass before moving on) |
| --- | --- | --- |
| Week 1 | Foundations & freeze: simulator + environment + reproducible repo | One full trace runs at a fixed seed; 3 diagnostic plots |
| Week 2 | Prediction & review: XGBoost + calibration + review routing | 5-fold CV, calibration, review-threshold sweep |
| Week 3 | Scheduling & architecture: PPO + 5 baselines + 5 ablations + sensitivity | Auditable action traces + statistical significance |
| Week 4 | Paper & archive: 8-10 pp draft + reproducibility package | Advisor pre-review pass; zero Chinese in deliverables |

# 3. Weekly Execution Plans

## Week 1 - Foundations and freeze (40 h)

| Day | Time | Task | Deliverable / Gate |
| --- | --- | --- | --- |
| W1D1 | 2 h | Write spec.md: 3 core claims, each mapped to an experiment number; a 'must NOT claim' list; the 4-agent message contract diagram | spec.md committed |
| W1D2 | 6 h | Build simulation data generator: normal + focus-drift degradation; all laser-welding state variables; seeded | raw_stream.csv generated |
| W1D3 | 8 h | Implement Machine/IoT Agent (validation + provenance), feature vector construction, train/test split | feature_vector.csv + provenance tags |
| W1D4 | 8 h | Implement Gymnasium-like environment: state, 5 actions, reward, resource constraints, feedback loop | env passes sanity checks |
| W1D5 | 8 h | Repo + experiment harness: config files, seed control, logging, first naive baseline (random + rule-based) | repo reproducible at fixed seed |
| W1D6 | 6 h | Unit tests + 3 diagnostic plots (urgency vs time; feature distributions; reward trace) | plots in report/figures |
| W1D7 | 2 h | Checkpoint: rerun entire pipeline from a clean clone; W1 retrospective | gate passed or scope cut |

## Week 2 - Prediction and human review (40 h)

| Day | Time | Task | Deliverable / Gate |
| --- | --- | --- | --- |
| W2D1 | 8 h | Train XGBoost urgency predictor; 5-fold CV; tune hyperparameters | CV MAE/RMSE/R2 logged |
| W2D2 | 6 h | Feature importance with SHAP; compare to physical expectations (focus drift, plasma, melt pool, back-reflection, thermal) | SHAP plots + plausibility notes |
| W2D3 | 8 h | Implement uncertainty proxy (predictive interval / ensemble disagreement / OOD score); measure calibration (ECE, coverage) | calibration plot |
| W2D4 | 8 h | Build review-trigger logic: thresholds, medium severity, high uncertainty, conflicting indicators, resource conflict | review router implemented |
| W2D5 | 6 h | Review-threshold sweep: review rate, override rate, critical failures avoided, operator burden | threshold sweep table + plot |
| W2D6 | 2 h | Compare no-review / random-review / uncertainty-triggered / all-review at equal review budget | E4 result table |
| W2D7 | 2 h | Week 2 checkpoint; archive model + results; update spec.md status | gate passed |

## Week 3 - Scheduling and architecture (40 h)

| Day | Time | Task | Deliverable / Gate |
| --- | --- | --- | --- |
| W3D1 | 8 h | Implement PPO agent; hyperparameter sensitivity (clip range, GAE lambda, LR, entropy) | learning curves over >=5 seeds |
| W3D2 | 6 h | Reward ablation: safety only / +downtime / +cost / +load / full | reward ablation table |
| W3D3 | 8 h | Run 5 baselines: corrective (react at failure), fixed periodic, XGBoost-only alert, rule-based scheduler, PPO-only | baseline comparison table |
| W3D4 | 8 h | Run 5 ablations: remove review, remove PPO (rule scheduler), remove XGBoost (rule urgency), remove provenance, remove uncertainty trigger (review all medium) | ablation table |
| W3D5 | 6 h | Sensitivity: sensor noise, missing modality, concept drift, OOD, scarce resources, maintenance delay | sensitivity plots |
| W3D6 | 2 h | Auditability: 100% trace completeness + 10 counterfactual tests (change one feature, check plausible cascade) | audit score + counterfactual log |
| W3D7 | 2 h | Week 3 checkpoint; freeze all figures and result numbers | gate passed |

## Week 4 - Paper and archive (40 h)

| Day | Time | Task | Deliverable / Gate |
| --- | --- | --- | --- |
| W4D1 | 8 h | Draft introduction + related work + contributions; re-read target conference template | Sections 1-2 complete |
| W4D2 | 8 h | Draft framework + methodology sections; reproduce all key tables from results | Sections 3-4 complete |
| W4D3 | 8 h | Draft experiments/results + validation discussion; assemble all figures | Sections 5-6 complete |
| W4D4 | 6 h | Conclusion, limitations, future work; full proofread for language + claim calibration | full draft 8-10 pp |
| W4D5 | 6 h | Build reproducibility package: generator, training scripts, configs, logs, Dockerfile/requirements, README | zip archive runs from clean checkout |
| W4D6 | 2 h | Advisor pre-review pass; address blocking comments only | review notes filed |
| W4D7 | 2 h | Final check: zero Chinese in code/comments/paper; final commit + tag | v1.0-submission-ready |

# 4. The Minimum Evidence Set (9 Experiments)

These are non-negotiable. E1 must precede everything; E2, E4, E5, E6, E9 are the protected core if time runs short.

| ID | Experiment | Design | Key metric | Week |
| --- | --- | --- | --- | --- |
| E1 | Simulation validity | Latent degradation model + induced faults (focus drift, lens contamination, gas, positioning); normal/degradation/OOD splits | Physical plausibility; fault separation | W1 |
| E2 | XGBoost urgency | 5-fold CV; MAE/RMSE/R2; SHAP; model comparison (RF, LightGBM, MLP) | Low error; SHAP matches physics | W2 |
| E3 | Uncertainty calibration | Quantile regression / ensemble / conformal / OOD; ECE and coverage | Error correlates with uncertainty | W2 |
| E4 | Review routing | No-review / random / uncertainty-triggered / all-review at equal budget | Better safety at lower burden | W2 |
| E5 | Full vs baselines | Corrective, periodic, alert-only, rule, PPO-only | Reward + audit + review coverage | W3 |
| E6 | Ablations | Remove review, PPO, XGBoost, provenance, trigger | Each component adds value | W3 |
| E7 | Sensitivity | Noise, missing modality, drift, OOD, scarce resources, delay | Graceful degradation | W3 |
| E8 | Auditability | 100% trace completeness + 10 counterfactuals | Every action reconstructable | W3 |
| E9 | Statistical validity | >=5 seeds; mean +/- 95% CI; paired bootstrap/Wilcoxon | Significant, reproducible | W3 |

# 5. Tracking Table (fill in during execution)

| ID | Experiment | Status | Actual result / notes |
| --- | --- | --- | --- |
| E1 | Simulation validity |  |  |
| E2 | XGBoost urgency |  |  |
| E3 | Uncertainty calibration |  |  |
| E4 | Review routing |  |  |
| E5 | Full vs baselines |  |  |
| E6 | Ablations |  |  |
| E7 | Sensitivity |  |  |
| E8 | Auditability |  |  |
| E9 | Statistical validity |  |  |

Status values: Not started / Running / Done / At risk. The highlighted column is for the student to fill in as work progresses.

# 6. Execution Rules

# 7. Claim-to-Evidence Mapping (for the paper's Validation section)

| Claim | Experiment | Accept criterion |
| --- | --- | --- |
| Urgency prediction is valid | XGBoost CV + SHAP + uncertainty (E2, E3) | MAE/RMSE, calibration, SHAP plausibility |
| Selective review works | Threshold sweep + random-review control (E4) | Review rate, override accuracy, failures avoided |
| PPO scheduling works | Baseline + reward ablation (E5 + W3D1/D2) | Failures, downtime, cost, reward |
| Architecture adds value | Full vs ablations (E5, E6) | Reward + audit + review coverage |
| Framework is robust | Sensitivity (E7) | Graceful metric degradation |
| Coordination is auditable | Auditability (E8) | 100% trace completeness |
| Results are reproducible | Statistical validity (E9) | >=5 seeds, 95% CI, paired tests |

# 8. Success criteria

- Full ORCHESTRA achieves planning performance comparable to PPO-only while routing a material subset of cases through expert review.

- Each ablated component shows a measurable contribution (no free riders).

- Uncertainty-triggered review outperforms random review at the same review budget.

- All metrics reported with 95% confidence intervals over at least 5 seeds.

- Every decision has a complete, reconstructable audit trace.

- The draft and all code/comments are entirely in English, with no Chinese text.